## Programme
WITHNELL STATION BRIDGE - 1223
Quarter Commencing |  | 2027 Q1 | 2027 Q2 | 2027 Q3 | 2027 Q4 | 2028 Q1 | 2028 Q2 | 2028 Q3 | 2028 Q4 | 2029 Q1 | 2029 Q2 | 2029 Q3 | 2029 Q4 | 2030 Q1 | 2030 Q2 | 2030 Q3 | 2030 Q4 | 2031 Q1 | 2031 Q2 | 2031 Q3 | 2031 Q4 | 2032 Q1 | 2032 Q2 | 2032 Q3 | 2032 Q4
Number Of Quarters = | 24 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Activity | Duration
Phase
Prep and Brief | bar: 2027 Q1
Prelimnary Design | bar: 2027 Q2 to 2027 Q3
Procurement | bar: 2027 Q4 to 2028 Q2
Detail Des + Construction | bar: 2028 Q3 to 2029 Q4
FLOAT | bar: 2030 Q1
Maintenance (Under Contract) | bar: 2030 Q2 to 2031 Q1
Contract Completion Operations | bar: 2030 Q1
Prep and Brief
Stakeholder Liaison | bar: 2027 Q1
Circulate Brief | bar: 2027 Q1
Confirm Brief / Gateway Review | bar: 2027 Q1
Prelimnary Design
Drawings | bar: 2027 Q2
Documents | bar: 2027 Q2 to 2027 Q3
Services Agreements | bar: 2027 Q2 to 2027 Q3
Ecological - Site Preliminary Works | bar: 2027 Q2 to 2028 Q2
Budget Check | bar: 2027 Q3
Value Engineering | bar: 2027 Q2 to 2027 Q3
Stakeholder Liaison | bar: 2027 Q2
Preliminary Design Freeze / Gateway Review | bar: 2027 Q3
Procurement
Agree Procurement Plan - Internal | bar: 2027 Q4
ITT | bar: 2027 Q4
Bidding | bar: 2027 Q4 to 2028 Q1
Assessment | bar: 2028 Q1
Gateway Review Meeting/s | bar: 2028 Q2
Award | bar: 2028 Q2
Detail Design + Construction
Detailed Design | bar: 2028 Q3 to 2028 Q4
Design Freeze | bar: 2029 Q1
Enabling / Prelim Works | bar: 2029 Q1 to 2029 Q2
Utility Diversions | bar: 2029 Q2 to 2029 Q3
Construction | bar: 2029 Q2 to 2029 Q4
Finishing Works | bar: 2029 Q4
Stakeholder Satisfaction Meetings | bar: 2028 Q4; 2029 Q2; 2029 Q4
FLOAT
FLOAT | bar: 2030 Q1
Contract Completion Operations | bar: 2030 Q1
Maintenance
1st Year Maintenance (Under Contract) | bar: 2030 Q2 to 2031 Q1
End of Maintenance Inspections | bar: 2031 Q1
Ongoing Maintenance | bar: 2031 Q2 to 2032 Q4

## Site Works (hidden)
Day Number |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Activity | Duration
Phase 1 Works
Site establishment | 1 | bar: 1
Repair to spalled sections | 2 | [25 empty] | Contract 1 | bar: 2 to 3
Repair to vertical cracks | 2 | [25 empty] | Contract 2 | bar: 3 to 4
Treat honeycombing | 1 | [25 empty] | Contract 1 potentially | bar: 4
De-mobilisation | 1 | bar: 5
Phase 2 Works
TM installed | 1 | bar: 6
TM maintained | 20 | bar: 6 to 25
Carriageway resurfacing | [26 empty] | This task is to be broken down into further sub-tasks when more about the process is known | bar: 6 to 25
Will road re-surfacing take place lane-by-lane or across the width of the road, re-surfacing down the road
Site Termination | [26 empty] | Ops to do this
Removal of TM | 1 | bar: 25
De-mobilisation | 1 | bar: 25

## _Helper (hidden)
#VALUE!
#VALUE!

## _Lists (hidden)
FinancialYears
26/27
27/28
28/29
29/30
30/31
31/32
32/33
33/34
34/35
StatusList
Planned